## Budget_Detail
Budget Detail
WBS_L1 | WBS_Code | WBS_Task | Cost_Item | Cost_Type | Unit | Quantity | Unit_Price_USD | Total_USD | Cost_Basis | Estimated_Labor_Hours | Labor_Rate_Assumption_USD_per_hr | Source_URL | Notes
2 | 1.2 | Project Governance & Controls | Project controls software & IT (scheduling, cost control) | Soft Cost | LS | 1 | 250000 | 250000 | Lump Sum / Allowance |  |  | https://www.bls.gov/ooh/business-and-financial/project-management-specialists.htm | Licensing + implementation + training (placeholder).
2 | 1.3 | Project Administration | Insurance (builder's risk, GL, professional liability) during construction | Soft Cost | LS | 1 | 3000000 | 3000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Benchmark-based placeholder; varies by contracts and risk profile.
2 | 1.3 | Project Administration | Owner/Developer PMO labor (PM, controls, HSE, admin) | Labor | FTE-month | 240 | 12500 | 3000000 | Unit-based Labor | 41600 | 72.1154 | https://www.bls.gov/ooh/business-and-financial/project-management-specialists.htm | Assume 8 FTE for 30 months at ~$150k/yr loaded rate (based on BLS PM specialist median + burden).
2 | 1.4 | Risk & Issue Management | Contingency reserve (10% of subtotal) | Soft Cost | LS | 1 | 47314800 | 47314800 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Applied as overall cost reserve for uncertainty.
2 | 1.4 | Risk & Issue Management | Management reserve (5% of subtotal) | Soft Cost | LS | 1 | 23657400 | 23657400 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Owner-controlled reserve.
3 | 2.2.1 | Negotiate land lease/purchase terms | Land option/lease payments during development & construction | Soft Cost | Acre-year | 1800 | 1000 | 1800000 | Unit-based Material/Service |  |  | https://www.sciencedirect.com/science/article/pii/S0301421525003416 | Assume 900 acres (≈6 acres/MW for 150 MW). Lease/option rate ~$1,000/acre-year based on reported ranges.
3 | 2.2.3 | Execute land agreements and record titles | Title, survey, easements legal work | Soft Cost | LS | 1 | 350000 | 350000 | Lump Sum / Allowance |  |  | https://docs.nlr.gov/docs/fy13osti/56290.pdf | Includes legal, title insurance, recording fees.
3 | 2.3.1 | Baseline environmental surveys | Baseline environmental surveys (flora/fauna, wetlands) | Soft Cost | LS | 1 | 600000 | 600000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
3 | 2.3.2 | Environmental Impact Assessment report | Environmental Impact Assessment and permitting support | Soft Cost | LS | 1 | 1200000 | 1200000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
3 | 2.3.3 | Public consultation and stakeholder engagement | Public consultation/stakeholder engagement | Soft Cost | LS | 1 | 200000 | 200000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
3 | 2.4.1 | Submit application | Zoning/local permit application fees | Soft Cost | LS | 1 | 250000 | 250000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
3 | 2.5.1 | Submit interconnection request to Dominion/PJM | Interconnection studies & queue deposits (utility/ISO) | Soft Cost | LS | 1 | 1500000 | 1500000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
4 | 3.1 | Conceptual Design | Conceptual engineering (site layout, preliminary SLDs) | Soft Cost | LS | 1 | 500000 | 500000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
4 | 3.2.1 | Issue for Submission | Permit/zoning design package preparation | Soft Cost | LS | 1 | 650000 | 650000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
4 | 3.3 | Detailed Electrical & Civil Design | Detailed electrical & civil design (IFC drawings) | Soft Cost | LS | 1 | 2000000 | 2000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
4 | 3.4 | BESS System Design | BESS system design (specs, layout, controls interfaces) | Soft Cost | LS | 1 | 750000 | 750000 | Lump Sum / Allowance |  |  | https://docs.nrel.gov/docs/fy25osti/93281.pdf
4 | 3.5 | SCADA & Communications Design | SCADA & communications design | Soft Cost | LS | 1 | 400000 | 400000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
4 | 3.6 | Design Reviews & Approvals | Independent design reviews (Owner's Engineer) | Soft Cost | LS | 1 | 1200000 | 1200000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
5 | 4.1 | Financial Modeling | Financial modeling and owner's cost estimation support | Soft Cost | LS | 1 | 250000 | 250000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
5 | 4.2 | Power Purchase Agreement | PPA negotiation legal & advisory fees | Soft Cost | LS | 1 | 800000 | 800000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
5 | 4.3 | Tax Equity & Capital Structure | Tax equity structuring & counsel | Soft Cost | LS | 1 | 900000 | 900000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
5 | 4.4 | Financial Close | Lender/financing fees and due diligence (IE, insurance advisor) | Soft Cost | LS | 1 | 1200000 | 1200000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
6 | 5.1 | Procurement Strategy & EPC | EPC procurement strategy development | Soft Cost | LS | 1 | 150000 | 150000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
6 | 5.2 | Vendor Selection | Vendor selection process (RFQs, evaluation, site visits) | Soft Cost | LS | 1 | 300000 | 300000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
6 | 5.3 | Contracting | Contract negotiation & drafting (EPC, supply, O&M) | Soft Cost | LS | 1 | 450000 | 450000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
6 | 5.4.1 | Monitor module/tracker/inverter manufacturing | Logistics & expediting: PV/module/tracker/inverter shipping management | Soft Cost | LS | 1 | 2500000 | 2500000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Freight forwarding + expediting services (placeholder).
6 | 5.4.2 | Monitor BESS container/PCS manufacturing | Logistics & expediting: BESS shipping management | Soft Cost | LS | 1 | 2000000 | 2000000 | Lump Sum / Allowance |  |  | https://docs.nrel.gov/docs/fy25osti/93281.pdf | Freight forwarding + expediting services (placeholder).
7 | 6.1.1 | Establish site offices, laydown areas, utilities | Temporary facilities: site offices, laydown, utilities | Direct Cost | LS | 1 | 4000000 | 4000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
7 | 6.1.2 | Site safety setup and access control | Site safety setup, traffic control, access control | Direct Cost | LS | 1 | 1200000 | 1200000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
7 | 6.2.1 | Clearing and grubbing | Clearing and grubbing | Direct Cost | Acre | 900 | 6000 | 5400000 | Unit-based Material/Service |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Unit cost placeholder; site-specific.
7 | 6.2.2 | Grading and drainage features | Mass grading and drainage features | Direct Cost | MWdc | 150 | 80000 | 12000000 | Unit-based Material/Service |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Parametric placeholder.
7 | 6.2.3 | Internal roads and access improvements | Internal roads and access improvements | Direct Cost | MWdc | 150 | 55000 | 8250000 | Unit-based Material/Service |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Parametric placeholder.
7 | 6.3.1.1 | Pile driving for tracker foundations | Pile driving for tracker foundations (labor + equipment) | Labor | MWdc | 150 | 80000 | 12000000 | Unit-based Labor | 160000 | 75 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Includes pile supply & driving.
7 | 6.3.1.2 | Inverter station foundations | Inverter station foundations | Direct Cost | Each | 50 | 40000 | 2000000 | Unit-based Material/Service |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Assume 50 inverter stations.
7 | 6.3.1.3 | Substation foundations | Substation foundations and yard prep | Direct Cost | LS | 1 | 3000000 | 3000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
7 | 6.3.2 | Mounting structures installation | Mounting structures installation labor (mechanical) | Labor | MWdc | 150 | 50000 | 7500000 | Unit-based Labor | 100000 | 75 | https://www.bls.gov/ooh/management/construction-managers.htm | Crew labor only; tracker hardware cost accounted separately.
7 | 6.4.1 | Perimeter fencing and gates | Perimeter fencing and gates | Direct Cost | Mile | 5 | 600000 | 3000000 | Unit-based Material/Service |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Assume ~5 miles perimeter; site-specific.
7 | 6.4.2 | Security cameras and lighting infrastructure | Security cameras and lighting infrastructure | Direct Cost | LS | 1 | 4000000 | 4000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
8 | 7.1.1.1 | Tracker/racking system installation | Tracker/racking hardware supply (single-axis) | Direct Cost | MWdc | 150 | 120000 | 18000000 | Unit-based Material/Service |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf | Unit-cost placeholder calibrated to utility-scale PV benchmarks.
8 | 7.1.1.2 | PV module installation | PV module installation labor | Labor | MWdc | 150 | 25000 | 3750000 | Unit-based Labor | 50000 | 75 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm | Crew labor only.
8 | 7.1.1.2 | PV module installation | PV modules supply (bifacial ~530W modules) | Direct Cost | Module | 283019 | 132.4999 | 37500000 | Unit-based Material/Service |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf | Module cost derived from utility-scale PV benchmark; actual procurement depends on market/tariffs.
8 | 7.1.1.3 | Module stringing and torquing | Module stringing and torquing labor | Labor | MWdc | 150 | 18000 | 2700000 | Unit-based Labor | 36000 | 75 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
8 | 7.1.2 | DC cabling, combiner boxes, and junction boxes | DC cabling, combiner boxes, junction boxes (supply) | Direct Cost | MWdc | 150 | 70000 | 10500000 | Unit-based Material/Service |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf
8 | 7.2.1.2 | Inverter equipment installation | Central inverters (supply) | Direct Cost | Each | 50 | 180000 | 9000000 | Unit-based Material/Service |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf | Assume 50 inverter units total.
8 | 7.2.1.2 | Inverter equipment installation | Inverter equipment installation labor | Labor | Each | 50 | 30000 | 1500000 | Unit-based Labor | 20000 | 75 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
8 | 7.2.2 | Medium‑voltage cabling and terminations | Electrical installation labor (DC/AC collection) | Labor | MWdc | 150 | 60000 | 9000000 | Unit-based Labor | 105882.3529 | 85 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
8 | 7.2.2 | Medium‑voltage cabling and terminations | Medium-voltage cabling and terminations (supply) | Direct Cost | MWdc | 150 | 65000 | 9750000 | Unit-based Material/Service |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf
8 | 7.2.3 | Pad‑mounted and main step‑up transformer installation | Pad-mounted transformers and main step-up transformers (supply) | Direct Cost | LS | 1 | 12000000 | 12000000 | Lump Sum / Allowance |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf
8 | 7.3.2.1 | Main power transformer installation | Main power transformer (supply) | Direct Cost | Each | 1 | 8000000 | 8000000 | Unit-based Material/Service |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf
8 | 7.3.2.2 | Switchgear and protection equipment | Substation installation labor (erection, wiring, testing support) | Labor | LS | 1 | 5000000 | 5000000 | Lump Sum / Allowance | 58823.5294 | 85 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
8 | 7.3.2.2 | Switchgear and protection equipment | Switchgear, protection, relays (supply) | Direct Cost | LS | 1 | 6000000 | 6000000 | Lump Sum / Allowance |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf
8 | 7.3.2.3 | Control house and auxiliary systems | Control house & auxiliary systems (supply) | Direct Cost | LS | 1 | 4000000 | 4000000 | Lump Sum / Allowance |  |  | https://docs.nrel.gov/docs/fy25osti/92257.pdf
8 | 7.3.3 | Transmission line or tie‑in works to Dominion’s grid | Transmission line / tie-in works (materials + contractors) | Direct Cost | LS | 1 | 10000000 | 10000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
8 | 7.4.1 | BESS container/cabinet installation | BESS battery containers/packs (supply) | Direct Cost | kWh | 600000 | 200 | 120000000 | Unit-based Material/Service |  |  | https://docs.nrel.gov/docs/fy25osti/93281.pdf | Component of total installed cost; placeholder split.
8 | 7.4.1 | BESS container/cabinet installation | BESS installation labor (containers, PCS, cabling) | Labor | kWh | 600000 | 33.33 | 19998000 | Unit-based Labor | 249975 | 80 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm | ≈$20M total labor allocated over 600,000 kWh.
8 | 7.4.2.1 | BESS transformers and switchgear | BESS transformers and switchgear (supply) | Direct Cost | LS | 1 | 12000000 | 12000000 | Lump Sum / Allowance |  |  | https://docs.nrel.gov/docs/fy25osti/93281.pdf
8 | 7.4.2.2 | Power conversion system installation | BESS power conversion system (PCS) (supply) | Direct Cost | kW | 150000 | 200 | 30000000 | Unit-based Material/Service |  |  | https://docs.nrel.gov/docs/fy25osti/93281.pdf
8 | 7.4.2.3 | Battery management system and controls | Battery management system (BMS) + EMS/controls (supply) | Direct Cost | LS | 1 | 8000000 | 8000000 | Lump Sum / Allowance |  |  | https://docs.nrel.gov/docs/fy25osti/93281.pdf
8 | 7.4.3 | BESS HVAC, fire protection, and safety systems installation | BESS HVAC, fire protection, and safety systems (supply + install) | Direct Cost | LS | 1 | 10000000 | 10000000 | Lump Sum / Allowance |  |  | https://docs.nrel.gov/docs/fy25osti/93281.pdf
9 | 8.1 | SCADA Hardware Installation | SCADA servers, RTUs/PLCs, meters, weather station (supply) | Direct Cost | LS | 1 | 5500000 | 5500000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
9 | 8.2 | Communications Network | Communications network (fiber, switches, radios) | Direct Cost | LS | 1 | 3000000 | 3000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
9 | 8.3.1 | Integrate PV and BESS controls | Integrate PV and BESS controls (engineering + configuration) | Labor | LS | 1 | 1500000 | 1500000 | Lump Sum / Allowance | 20798.6689 | 72.12 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
9 | 8.3.2 | Interface with utility control/dispatch systems | Utility interface (SCADA points list, ICCP/dispatch) integration | Labor | LS | 1 | 750000 | 750000 | Lump Sum / Allowance | 7894.7368 | 95 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
9 | 8.3.3 | Interface with Amazon’s energy monitoring platform | Amazon energy monitoring interface integration | Labor | LS | 1 | 750000 | 750000 | Lump Sum / Allowance | 10000 | 75 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
10 | 9.1 | Pre‑Commissioning Electrical Tests | Pre-commissioning electrical tests (megger, hi-pot, continuity) | Labor | LS | 1 | 800000 | 800000 | Lump Sum / Allowance | 9411.7647 | 85 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
10 | 9.2.1 | PV array energization and staged startup | PV array energization and staged startup services | Labor | LS | 1 | 900000 | 900000 | Lump Sum / Allowance | 12000 | 75 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
10 | 9.2.2 | BESS commissioning and performance tests | BESS commissioning and performance testing services | Labor | LS | 1 | 2000000 | 2000000 | Lump Sum / Allowance | 23529.4118 | 85 | https://docs.nrel.gov/docs/fy25osti/93281.pdf
10 | 9.2.3 | SCADA and communications system testing | SCADA and communications system testing | Labor | LS | 1 | 600000 | 600000 | Lump Sum / Allowance | 6315.7895 | 95 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
10 | 9.4 | Grid Interconnection | Grid interconnection witness tests, relay settings, compliance | Soft Cost | LS | 1 | 1200000 | 1200000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
10 | 9.4 | Grid Interconnection | Network upgrades / interconnection facilities (utility scope allowance) | Direct Cost | LS | 1 | 15000000 | 15000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Highly site/utility dependent; placeholder allowance.
11 | 10.1 | As‑Built Documentation | As-built drawings, redlines, final documentation | Soft Cost | LS | 1 | 600000 | 600000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
11 | 10.2 | Operation & Maitenance Setup | Initial spares & O&M tools (recommended spares kit) | Direct Cost | LS | 1 | 2000000 | 2000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
11 | 10.3 | Training & Knowledge Transfer | Training & knowledge transfer (PV + BESS + SCADA) | Soft Cost | LS | 1 | 300000 | 300000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
11 | 10.4 | Project Closeout | Demobilization, cleanup, closeout admin | Soft Cost | LS | 1 | 1000000 | 1000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
11 | 10.4 | Project Closeout | Warranty reserve / punch list corrections allowance | Soft Cost | LS | 1 | 2000000 | 2000000 | Lump Sum / Allowance |  |  | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Note on A1: Built from the uploaded Helios workbook. Quantity was normalized to make each detail line mathematically consistent. Source URLs retained from the original estimate.

## Validation_Checks
Validation Checks
WBS_Code | Cost_Item | Original_Unit | Original_Qty | Original_Unit_Price | Original_Total | Normalized_Qty | Normalized_Unit_Price | Normalized_Total | Validation_Diff_USD
1.3 | Owner/Developer PMO labor (PM, controls, HSE, admin) | FTE-month | 241 | 12500 | 3000000 | 240 | 12500 | 3000000 | 0
1.2 | Project controls software & IT (scheduling, cost control) | Lot | 2 | 250000 | 250000 | 1 | 250000 | 250000 | 0
1.3 | Insurance (builder's risk, GL, professional liability) during construction | Lot | 2 | 3000000 | 3000000 | 1 | 3000000 | 3000000 | 0
2.2.1 | Land option/lease payments during development & construction | Acre-year | 1801 | 1000 | 1800000 | 1800 | 1000 | 1800000 | 0
2.2.3 | Title, survey, easements legal work | Lot | 2 | 350000 | 350000 | 1 | 350000 | 350000 | 0
2.3.1 | Baseline environmental surveys (flora/fauna, wetlands) | Lot | 2 | 600000 | 600000 | 1 | 600000 | 600000 | 0
2.3.2 | Environmental Impact Assessment and permitting support | Lot | 2 | 1200000 | 1200000 | 1 | 1200000 | 1200000 | 0
2.3.3 | Public consultation/stakeholder engagement | Lot | 2 | 200000 | 200000 | 1 | 200000 | 200000 | 0
2.4.1 | Zoning/local permit application fees | Lot | 2 | 250000 | 250000 | 1 | 250000 | 250000 | 0
2.5.1 | Interconnection studies & queue deposits (utility/ISO) | Lot | 2 | 1500000 | 1500000 | 1 | 1500000 | 1500000 | 0
3.1 | Conceptual engineering (site layout, preliminary SLDs) | Lot | 2 | 500000 | 500000 | 1 | 500000 | 500000 | 0
3.2.1 | Permit/zoning design package preparation | Lot | 2 | 650000 | 650000 | 1 | 650000 | 650000 | 0
3.3 | Detailed electrical & civil design (IFC drawings) | Lot | 2 | 2000000 | 2000000 | 1 | 2000000 | 2000000 | 0
3.4 | BESS system design (specs, layout, controls interfaces) | Lot | 2 | 750000 | 750000 | 1 | 750000 | 750000 | 0
3.5 | SCADA & communications design | Lot | 2 | 400000 | 400000 | 1 | 400000 | 400000 | 0
3.6 | Independent design reviews (Owner's Engineer) | Lot | 2 | 1200000 | 1200000 | 1 | 1200000 | 1200000 | 0
4.1 | Financial modeling and owner's cost estimation support | Lot | 2 | 250000 | 250000 | 1 | 250000 | 250000 | 0
4.2 | PPA negotiation legal & advisory fees | Lot | 2 | 800000 | 800000 | 1 | 800000 | 800000 | 0
4.3 | Tax equity structuring & counsel | Lot | 2 | 900000 | 900000 | 1 | 900000 | 900000 | 0
4.4 | Lender/financing fees and due diligence (IE, insurance advisor) | Lot | 2 | 1200000 | 1200000 | 1 | 1200000 | 1200000 | 0
5.1 | EPC procurement strategy development | Lot | 2 | 150000 | 150000 | 1 | 150000 | 150000 | 0
5.2 | Vendor selection process (RFQs, evaluation, site visits) | Lot | 2 | 300000 | 300000 | 1 | 300000 | 300000 | 0
5.3 | Contract negotiation & drafting (EPC, supply, O&M) | Lot | 2 | 450000 | 450000 | 1 | 450000 | 450000 | 0
5.4.1 | Logistics & expediting: PV/module/tracker/inverter shipping management | Lot | 2 | 2500000 | 2500000 | 1 | 2500000 | 2500000 | 0
5.4.2 | Logistics & expediting: BESS shipping management | Lot | 2 | 2000000 | 2000000 | 1 | 2000000 | 2000000 | 0
6.1.1 | Temporary facilities: site offices, laydown, utilities | Lot | 2 | 4000000 | 4000000 | 1 | 4000000 | 4000000 | 0
6.1.2 | Site safety setup, traffic control, access control | Lot | 2 | 1200000 | 1200000 | 1 | 1200000 | 1200000 | 0
6.2.1 | Clearing and grubbing | Acre | 901 | 6000 | 5400000 | 900 | 6000 | 5400000 | 0
6.2.2 | Mass grading and drainage features | MWdc | 151 | 80000 | 12000000 | 150 | 80000 | 12000000 | 0
6.2.3 | Internal roads and access improvements | MWdc | 151 | 55000 | 8250000 | 150 | 55000 | 8250000 | 0
6.3.1.1 | Pile driving for tracker foundations (labor + equipment) | MWdc | 151 | 80000 | 12000000 | 150 | 80000 | 12000000 | 0
6.3.1.2 | Inverter station foundations | Each | 51 | 40000 | 2000000 | 50 | 40000 | 2000000 | 0
6.3.1.3 | Substation foundations and yard prep | Lot | 2 | 3000000 | 3000000 | 1 | 3000000 | 3000000 | 0
6.3.2 | Mounting structures installation labor (mechanical) | MWdc | 151 | 50000 | 7500000 | 150 | 50000 | 7500000 | 0
6.4.1 | Perimeter fencing and gates | Mile | 6 | 600000 | 3000000 | 5 | 600000 | 3000000 | 0
6.4.2 | Security cameras and lighting infrastructure | Lot | 2 | 4000000 | 4000000 | 1 | 4000000 | 4000000 | 0
7.1.1.1 | Tracker/racking hardware supply (single-axis) | MWdc | 151 | 120000 | 18000000 | 150 | 120000 | 18000000 | 0
7.1.1.2 | PV modules supply (bifacial ~530W modules) | Module | 283020 | 132.4999 | 37500000 | 283019 | 132.4999 | 37500000 | 0
7.1.1.2 | PV module installation labor | MWdc | 151 | 25000 | 3750000 | 150 | 25000 | 3750000 | 0
7.1.1.3 | Module stringing and torquing labor | MWdc | 151 | 18000 | 2700000 | 150 | 18000 | 2700000 | 0
7.1.2 | DC cabling, combiner boxes, junction boxes (supply) | MWdc | 151 | 70000 | 10500000 | 150 | 70000 | 10500000 | 0
7.2.1.2 | Central inverters (supply) | Each | 51 | 180000 | 9000000 | 50 | 180000 | 9000000 | 0
7.2.1.2 | Inverter equipment installation labor | Each | 51 | 30000 | 1500000 | 50 | 30000 | 1500000 | 0
7.2.2 | Medium-voltage cabling and terminations (supply) | MWdc | 151 | 65000 | 9750000 | 150 | 65000 | 9750000 | 0
7.2.3 | Pad-mounted transformers and main step-up transformers (supply) | Lot | 2 | 12000000 | 12000000 | 1 | 12000000 | 12000000 | 0
7.3.2.1 | Main power transformer (supply) | Each | 2 | 8000000 | 8000000 | 1 | 8000000 | 8000000 | 0
7.3.2.2 | Switchgear, protection, relays (supply) | Lot | 2 | 6000000 | 6000000 | 1 | 6000000 | 6000000 | 0
7.3.2.3 | Control house & auxiliary systems (supply) | Lot | 2 | 4000000 | 4000000 | 1 | 4000000 | 4000000 | 0
7.3.3 | Transmission line / tie-in works (materials + contractors) | Lot | 2 | 10000000 | 10000000 | 1 | 10000000 | 10000000 | 0
7.2.2 | Electrical installation labor (DC/AC collection) | MWdc | 151 | 60000 | 9000000 | 150 | 60000 | 9000000 | 0
7.3.2.2 | Substation installation labor (erection, wiring, testing support) | Lot | 2 | 5000000 | 5000000 | 1 | 5000000 | 5000000 | 0
7.4.1 | BESS battery containers/packs (supply) | kWh | 600001 | 200 | 120000000 | 600000 | 200 | 120000000 | 0
7.4.2.2 | BESS power conversion system (PCS) (supply) | kW | 150001 | 200 | 30000000 | 150000 | 200 | 30000000 | 0
7.4.2.1 | BESS transformers and switchgear (supply) | Lot | 2 | 12000000 | 12000000 | 1 | 12000000 | 12000000 | 0
7.4.2.3 | Battery management system (BMS) + EMS/controls (supply) | Lot | 2 | 8000000 | 8000000 | 1 | 8000000 | 8000000 | 0
7.4.3 | BESS HVAC, fire protection, and safety systems (supply + install) | Lot | 2 | 10000000 | 10000000 | 1 | 10000000 | 10000000 | 0
7.4.1 | BESS installation labor (containers, PCS, cabling) | kWh | 600001 | 33.33 | 19998000 | 600000 | 33.33 | 19998000 | 0
8.1 | SCADA servers, RTUs/PLCs, meters, weather station (supply) | Lot | 2 | 5500000 | 5500000 | 1 | 5500000 | 5500000 | 0
8.2 | Communications network (fiber, switches, radios) | Lot | 2 | 3000000 | 3000000 | 1 | 3000000 | 3000000 | 0
8.3.1 | Integrate PV and BESS controls (engineering + configuration) | Lot | 2 | 1500000 | 1500000 | 1 | 1500000 | 1500000 | 0
8.3.2 | Utility interface (SCADA points list, ICCP/dispatch) integration | Lot | 2 | 750000 | 750000 | 1 | 750000 | 750000 | 0
8.3.3 | Amazon energy monitoring interface integration | Lot | 2 | 750000 | 750000 | 1 | 750000 | 750000 | 0
9.1 | Pre-commissioning electrical tests (megger, hi-pot, continuity) | Lot | 2 | 800000 | 800000 | 1 | 800000 | 800000 | 0
9.2.1 | PV array energization and staged startup services | Lot | 2 | 900000 | 900000 | 1 | 900000 | 900000 | 0
9.2.2 | BESS commissioning and performance testing services | Lot | 2 | 2000000 | 2000000 | 1 | 2000000 | 2000000 | 0
9.2.3 | SCADA and communications system testing | Lot | 2 | 600000 | 600000 | 1 | 600000 | 600000 | 0
9.4 | Grid interconnection witness tests, relay settings, compliance | Lot | 2 | 1200000 | 1200000 | 1 | 1200000 | 1200000 | 0
9.4 | Network upgrades / interconnection facilities (utility scope allowance) | Lot | 2 | 15000000 | 15000000 | 1 | 15000000 | 15000000 | 0
10.1 | As-built drawings, redlines, final documentation | Lot | 2 | 600000 | 600000 | 1 | 600000 | 600000 | 0
10.2 | Initial spares & O&M tools (recommended spares kit) | Lot | 2 | 2000000 | 2000000 | 1 | 2000000 | 2000000 | 0
10.3 | Training & knowledge transfer (PV + BESS + SCADA) | Lot | 2 | 300000 | 300000 | 1 | 300000 | 300000 | 0
10.4 | Demobilization, cleanup, closeout admin | Lot | 2 | 1000000 | 1000000 | 1 | 1000000 | 1000000 | 0
10.4 | Warranty reserve / punch list corrections allowance | Lot | 2 | 2000000 | 2000000 | 1 | 2000000 | 2000000 | 0
1.4 | Contingency reserve (approved budget rebalancing reserve) | Lot | 1 | 26852000 | 26852000 | 1 | 26852000 | 26852000 | 0
1.4 | Management reserve (removed; included in approved contingency total) | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Task_Budget
Task Budget
Phase | Phase_Name | WBS_Code | Task_Name | Start | Finish | Duration_Days | Budget_USD
1 | Project Management | 1.1 | Project Initiation & Charter | 2026-11-02 | 2026-11-13 | 11 | 0
1 | Project Management | 1.2 | Project Governance & Controls | 2026-11-16 | 2026-12-04 | 18 | 250000
1 | Project Management | 1.3 | Project Administration | 2026-12-07 | 2026-12-22 | 15 | 6000000
1 | Project Management | 1.4 | Contingency Reserve - Approved Budget Rebalance | 2026-11-02 | 2030-12-30 | 1519 | 26852000
2 | Development, Land & Permitting | 2.1 | Site Identification & Feasibility | 2026-11-16 | 2026-12-25 | 39 | 0
2 | Development, Land & Permitting | 2.2.1 | Negotiate land lease/purchase terms | 2026-12-27 | 2027-03-19 | 82 | 1800000
2 | Development, Land & Permitting | 2.2.2 | Secure easements and access rights | 2027-03-22 | 2027-05-14 | 53 | 0
2 | Development, Land & Permitting | 2.2.3 | Execute land agreements and record titles | 2027-05-17 | 2027-06-11 | 25 | 350000
2 | Development, Land & Permitting | 2.3.1 | Baseline environmental surveys | 2026-12-27 | 2027-02-19 | 54 | 600000
2 | Development, Land & Permitting | 2.3.2 | Environmental Impact Assessment report | 2027-02-22 | 2027-04-30 | 67 | 1200000
2 | Development, Land & Permitting | 2.3.3 | Public consultation and stakeholder engagement | 2027-05-03 | 2027-06-11 | 39 | 200000
2 | Development, Land & Permitting | 2.3.4 | Finalize mitigation measures | 2027-06-14 | 2027-07-09 | 25 | 0
2 | Development, Land & Permitting | 2.4.1 | Zoning & Local Permits - Submit application | 2027-07-12 | 2027-07-16 | 4 | 250000
2 | Development, Land & Permitting | 2.4.2 | Zoning & Local Permits - Revisions & Finalization | 2027-07-19 | 2027-10-29 | 102 | 0
2 | Development, Land & Permitting | 2.5.1 | Submit interconnection request to Dominion/PJM | 2026-12-27 | 2027-01-22 | 26 | 1500000
2 | Development, Land & Permitting | 2.5.2 | Support utility system impact and facilities studies | 2027-01-25 | 2027-07-09 | 165 | 0
2 | Development, Land & Permitting | 2.5.3 | Review and negotiate interconnection agreement | 2027-07-12 | 2027-10-01 | 81 | 0
3 | Engineering & Design | 3.1 | Conceptual Design | 2026-12-28 | 2027-02-19 | 53 | 500000
3 | Engineering & Design | 3.2.1 | Permit/Zoning Design Package - Issue for Submission | 2027-05-03 | 2027-07-09 | 67 | 650000
3 | Engineering & Design | 3.2.2 | Permit/Zoning Design Package - Revisions / Responses Comments | 2027-07-19 | 2027-10-29 | 102 | 0
3 | Engineering & Design | 3.3 | Detailed Electrical & Civil Design | 2027-11-01 | 2028-02-18 | 109 | 2000000
3 | Engineering & Design | 3.4 | BESS System Design | 2027-02-22 | 2027-05-14 | 81 | 750000
3 | Engineering & Design | 3.5 | SCADA & Communications Design | 2027-02-22 | 2027-04-30 | 67 | 400000
3 | Engineering & Design | 3.6 | Design Reviews & Approvals | 2028-02-21 | 2028-03-31 | 39 | 1200000
4 | Financing & Commercial | 4.1 | Financial Modeling | 2027-02-21 | 2027-04-02 | 40 | 250000
4 | Financing & Commercial | 4.2 | Power Purchase Agreement | 2027-04-05 | 2027-07-23 | 109 | 800000
4 | Financing & Commercial | 4.3 | Tax Equity & Capital Structure | 2027-07-26 | 2027-12-10 | 137 | 900000
4 | Financing & Commercial | 4.4 | Financial Close | 2028-04-03 | 2028-05-26 | 53 | 1200000
5 | Procurement & Manufacturing | 5.1 | Procurement Strategy & EPC | 2027-04-04 | 2027-04-30 | 26 | 150000
5 | Procurement & Manufacturing | 5.2 | Vendor Selection | 2028-04-03 | 2028-06-23 | 81 | 300000
5 | Procurement & Manufacturing | 5.3 | Contracting | 2028-06-26 | 2028-08-04 | 39 | 450000
5 | Procurement & Manufacturing | 5.4.1 | Monitor module/tracker/inverter manufacturing | 2028-08-06 | 2028-11-24 | 110 | 2500000
5 | Procurement & Manufacturing | 5.4.2 | Monitor BESS container/PCS manufacturing | 2028-08-06 | 2028-12-22 | 138 | 2000000
5 | Procurement & Manufacturing | 5.4.3 | Monitor main transformer manufacturing and delivery | 2028-08-06 | 2029-08-03 | 362 | 0
6 | Civil & Structural Construction | 6.1.1 | Establish site offices, laydown areas, utilities | 2028-08-07 | 2028-08-28 | 21 | 4000000
6 | Civil & Structural Construction | 6.1.2 | Site safety setup and access control | 2028-08-28 | 2028-09-08 | 11 | 1200000
6 | Civil & Structural Construction | 6.2.1 | Clearing and grubbing | 2028-09-10 | 2028-10-06 | 26 | 5400000
6 | Civil & Structural Construction | 6.2.2 | Grading and drainage features | 2028-10-09 | 2028-11-17 | 39 | 12000000
6 | Civil & Structural Construction | 6.2.3 | Internal roads and access improvements | 2028-11-20 | 2028-12-22 | 32 | 8250000
6 | Civil & Structural Construction | 6.3.1.1 | Pile driving for tracker foundations | 2028-11-19 | 2029-02-23 | 96 | 12000000
6 | Civil & Structural Construction | 6.3.1.2 | Inverter station foundations | 2028-11-19 | 2028-12-29 | 40 | 2000000
6 | Civil & Structural Construction | 6.3.1.3 | Substation foundations | 2028-11-19 | 2029-01-12 | 54 | 3000000
6 | Civil & Structural Construction | 6.3.2 | Mounting structures installation | 2029-02-26 | 2029-05-04 | 67 | 7500000
6 | Civil & Structural Construction | 6.4.1 | Perimeter fencing and gates | 2028-12-24 | 2029-01-19 | 26 | 3000000
6 | Civil & Structural Construction | 6.4.2 | Security cameras and lighting infrastructure | 2029-01-22 | 2029-02-09 | 18 | 4000000
7 | Electrical / PV / BESS Installation | 7.1.1.1 | Tracker/racking system installation | 2029-05-07 | 2029-07-30 | 84 | 18000000
7 | Electrical / PV / BESS Installation | 7.1.1.2 | PV module installation | 2029-07-31 | 2029-11-19 | 111 | 41250000
7 | Electrical / PV / BESS Installation | 7.1.1.3 | Module stringing and torquing | 2029-11-20 | 2030-01-14 | 55 | 2700000
7 | Electrical / PV / BESS Installation | 7.1.2 | DC cabling, combiner boxes, and junction boxes | 2030-01-15 | 2030-03-25 | 69 | 10500000
7 | Electrical / PV / BESS Installation | 7.2.1.1 | Central inverter foundation/mounting | 2029-01-01 | 2029-01-26 | 25 | 0
7 | Electrical / PV / BESS Installation | 7.2.1.2 | Inverter equipment installation | 2029-01-29 | 2029-03-12 | 42 | 10500000
7 | Electrical / PV / BESS Installation | 7.2.1.3 | DC/AC connections complete | 2030-03-26 | 2030-04-26 | 31 | 0
7 | Electrical / PV / BESS Installation | 7.2.2 | Medium-voltage cabling and terminations | 2030-04-29 | 2030-07-05 | 67 | 18750000
7 | Electrical / PV / BESS Installation | 7.2.3 | Pad-mounted and main step-up transformer installation | 2029-03-13 | 2029-05-04 | 52 | 12000000
7 | Electrical / PV / BESS Installation | 7.3.1 | Substation civil foundations | 2029-01-15 | 2029-02-23 | 39 | 0
7 | Electrical / PV / BESS Installation | 7.3.2.1 | Main power transformer installation | 2029-08-06 | 2029-09-14 | 39 | 8000000
7 | Electrical / PV / BESS Installation | 7.3.2.2 | Switchgear and protection equipment | 2029-08-06 | 2029-09-28 | 53 | 11000000
7 | Electrical / PV / BESS Installation | 7.3.2.3 | Control house and auxiliary systems | 2029-02-26 | 2029-04-05 | 38 | 4000000
7 | Electrical / PV / BESS Installation | 7.3.3 | Transmission line or tie-in works to Dominion's grid | 2029-10-01 | 2029-12-21 | 81 | 10000000
7 | Electrical / PV / BESS Installation | 7.4.1 | BESS container/cabinet installation | 2028-12-25 | 2029-02-02 | 39 | 139998000
7 | Electrical / PV / BESS Installation | 7.4.2.1 | BESS transformers and switchgear | 2029-02-05 | 2029-03-09 | 32 | 12000000
7 | Electrical / PV / BESS Installation | 7.4.2.2 | Power conversion system installation | 2029-02-05 | 2029-03-09 | 32 | 30000000
7 | Electrical / PV / BESS Installation | 7.4.2.3 | Battery management system and controls | 2029-03-12 | 2029-04-06 | 25 | 8000000
7 | Electrical / PV / BESS Installation | 7.4.3 | BESS HVAC, fire protection, and safety systems installation | 2029-02-05 | 2029-03-09 | 32 | 10000000
8 | SCADA & Controls Integration | 8.1 | SCADA Hardware Installation | 2029-04-09 | 2029-05-04 | 25 | 5500000
8 | SCADA & Controls Integration | 8.2 | Communications Network | 2029-05-07 | 2029-06-08 | 32 | 3000000
8 | SCADA & Controls Integration | 8.3.1 | Integrate PV and BESS controls | 2030-04-29 | 2030-05-17 | 18 | 1500000
8 | SCADA & Controls Integration | 8.3.2 | Interface with utility control/dispatch systems | 2030-05-20 | 2030-06-07 | 18 | 750000
8 | SCADA & Controls Integration | 8.3.3 | Interface with Amazon's energy monitoring platform | 2030-05-20 | 2030-05-31 | 11 | 750000
9 | Commissioning & Interconnection | 9.1 | Pre-Commissioning Electrical Tests | 2030-07-08 | 2030-08-02 | 25 | 800000
9 | Commissioning & Interconnection | 9.2.1 | PV array energization and staged startup | 2030-08-05 | 2030-08-23 | 18 | 900000
9 | Commissioning & Interconnection | 9.2.2 | BESS commissioning and performance tests | 2030-08-05 | 2030-08-30 | 25 | 2000000
9 | Commissioning & Interconnection | 9.2.3 | SCADA and communications system testing | 2030-06-10 | 2030-06-21 | 11 | 600000
9 | Commissioning & Interconnection | 9.3 | Inspections & Permits Closeout | 2030-09-02 | 2030-09-20 | 18 | 0
9 | Commissioning & Interconnection | 9.4 | Grid Interconnection | 2030-09-23 | 2030-10-18 | 25 | 16200000
10 | Closeout & Handover | 10.1 | As-Built Documentation | 2030-10-21 | 2030-11-29 | 39 | 600000
10 | Closeout & Handover | 10.2 | Operation & Maintenance Setup | 2030-10-21 | 2030-11-15 | 25 | 2000000
10 | Closeout & Handover | 10.3 | Training & Knowledge Transfer | 2030-11-18 | 2030-12-02 | 14 | 300000
10 | Closeout & Handover | 10.4 | Project Closeout | 2030-12-03 | 2030-12-30 | 27 | 3000000

## Phase_Summary
Phase Summary
Phase | Phase_Name | Phase_Start | Phase_Finish | Task_Count | Budget_USD | Share_of_Total | Duration_Months
1 | Project Management | 2026-11-02 | 2030-12-30 | 4 | 33102000 | 6.62% | 49.9055
2 | Development, Land & Permitting | 2026-11-16 | 2027-10-29 | 13 | 5900000 | 1.18% | 11.4004
3 | Engineering & Design | 2026-12-28 | 2028-03-31 | 7 | 5500000 | 1.1% | 15.0801
4 | Financing & Commercial | 2027-02-21 | 2028-05-26 | 4 | 3150000 | 0.63% | 15.1129
5 | Procurement & Manufacturing | 2027-04-04 | 2029-08-03 | 6 | 5400000 | 1.08% | 27.9918
6 | Civil & Structural Construction | 2028-08-07 | 2029-05-04 | 11 | 62350000 | 12.47% | 8.8706
7 | Electrical / PV / BESS Installation | 2028-12-25 | 2030-07-05 | 19 | 346698000 | 69.34% | 18.2998
8 | SCADA & Controls Integration | 2029-04-09 | 2030-06-07 | 5 | 11500000 | 2.3% | 13.9302
9 | Commissioning & Interconnection | 2030-06-10 | 2030-10-18 | 6 | 20500000 | 4.1% | 4.271
10 | Closeout & Handover | 2030-10-21 | 2030-12-30 | 4 | 5900000 | 1.18% | 2.2998

## Monthly_Spend
Monthly Spend
Month | Monthly_Allocated_USD | Cumulative_USD
2026-11-01 | 709676.3158 | 709676.3158
2026-12-01 | 7078065.0569 | 7787741.3727
2027-01-01 | 3067369.7078 | 10855111.0805
2027-02-01 | 1762580.4345 | 12617691.515
2027-03-01 | 2161660.4068 | 14779351.9218
2027-04-01 | 1861532.3121 | 16640884.2339
2027-05-01 | 1525271.7589 | 18166155.9928
2027-06-01 | 1237997.1314 | 19404153.1241
2027-07-01 | 1090072.0475 | 20494225.1716
2027-08-01 | 749813.3867 | 21244038.5584
2027-09-01 | 725625.8581 | 21969664.4165
2027-10-01 | 749813.3867 | 22719477.8032
2027-11-01 | 1271080.4036 | 23990558.2068
2027-12-01 | 1176493.2286 | 25167051.4354
2028-01-01 | 1111275.8373 | 26278327.2727
2028-02-01 | 1109580.622 | 27387907.8947
2028-03-01 | 1477639.4737 | 28865547.3684
2028-04-01 | 1254634.9308 | 30120182.2992
2028-05-01 | 1238831.8856 | 31359014.1849
2028-06-01 | 670370.0257 | 32029384.2105
2028-07-01 | 896389.4737 | 32925773.6842
2028-08-01 | 5952325.7787 | 38878099.4629
2028-09-01 | 6637304.0361 | 45515403.499
2028-10-01 | 9791880.8374 | 55307284.3364
2028-11-01 | 12076616.2917 | 67383900.6281
2028-12-01 | 38693319.9088 | 106077220.5369
2029-01-01 | 118484618.8832 | 224561839.4201
2029-02-01 | 57528605.5533 | 282090444.9733
2029-03-01 | 34714027.9865 | 316804472.9598
2029-04-01 | 17644070.5566 | 334448543.5164
2029-05-01 | 10307475.0876 | 344756018.604
2029-06-01 | 7610187.588 | 352366206.192
2029-07-01 | 7268884.2216 | 359635090.4135
2029-08-01 | 22461346.4843 | 382096436.8978
2029-09-01 | 20082784.5308 | 402179221.4286
2029-10-01 | 15745537.9928 | 417924759.4214
2029-11-01 | 11716635.2696 | 429641394.691
2029-12-01 | 4603257.9406 | 434244652.6316
2030-01-01 | 3772639.4737 | 438017292.1053
2030-02-01 | 4694642.1053 | 442711934.2105
2030-03-01 | 4297639.4737 | 447009573.6842
2030-04-01 | 1239339.0093 | 448248912.6935
2030-05-01 | 11661223.065 | 459910135.7585
2030-06-01 | 9678348.2972 | 469588484.0557
2030-07-01 | 2664777.4827 | 472253261.5385
2030-08-01 | 3509177.9352 | 475762439.4737
2030-09-01 | 5514589.0688 | 481277028.5425
2030-10-01 | 12774177.9352 | 494051206.4777
2030-11-01 | 2378819.8381 | 496430026.3158
2030-12-01 | 3569973.6842 | 500000000

## Labor_Hours_Est
Labor Hours Est
WBS_L1 | WBS_Code | WBS_Task | Cost_Item | Cost_Type | Unit | Quantity | Unit_Price_USD | Total_USD | Cost_Basis | Estimated_Labor_Hours | Labor_Rate_Assumption_USD_per_hr | Source_URL | Notes
2 | 1.3 | Project Administration | Owner/Developer PMO labor (PM, controls, HSE, admin) | Labor | FTE-month | 240 | 12500 | 3000000 | Unit-based Labor | 41600 | 72.1154 | https://www.bls.gov/ooh/business-and-financial/project-management-specialists.htm | Assume 8 FTE for 30 months at ~$150k/yr loaded rate (based on BLS PM specialist median + burden).
7 | 6.3.1.1 | Pile driving for tracker foundations | Pile driving for tracker foundations (labor + equipment) | Labor | MWdc | 150 | 80000 | 12000000 | Unit-based Labor | 160000 | 75 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Includes pile supply & driving.
7 | 6.3.2 | Mounting structures installation | Mounting structures installation labor (mechanical) | Labor | MWdc | 150 | 50000 | 7500000 | Unit-based Labor | 100000 | 75 | https://www.bls.gov/ooh/management/construction-managers.htm | Crew labor only; tracker hardware cost accounted separately.
8 | 7.1.1.2 | PV module installation | PV module installation labor | Labor | MWdc | 150 | 25000 | 3750000 | Unit-based Labor | 50000 | 75 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm | Crew labor only.
8 | 7.1.1.3 | Module stringing and torquing | Module stringing and torquing labor | Labor | MWdc | 150 | 18000 | 2700000 | Unit-based Labor | 36000 | 75 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
8 | 7.2.1.2 | Inverter equipment installation | Inverter equipment installation labor | Labor | Each | 50 | 30000 | 1500000 | Unit-based Labor | 20000 | 75 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
8 | 7.2.2 | Medium‑voltage cabling and terminations | Electrical installation labor (DC/AC collection) | Labor | MWdc | 150 | 60000 | 9000000 | Unit-based Labor | 105882.3529 | 85 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
8 | 7.3.2.2 | Switchgear and protection equipment | Substation installation labor (erection, wiring, testing support) | Labor | LS | 1 | 5000000 | 5000000 | Lump Sum / Allowance | 58823.5294 | 85 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
8 | 7.4.1 | BESS container/cabinet installation | BESS installation labor (containers, PCS, cabling) | Labor | kWh | 600000 | 33.33 | 19998000 | Unit-based Labor | 249975 | 80 | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm | ≈$20M total labor allocated over 600,000 kWh.
9 | 8.3.1 | Integrate PV and BESS controls | Integrate PV and BESS controls (engineering + configuration) | Labor | LS | 1 | 1500000 | 1500000 | Lump Sum / Allowance | 20798.6689 | 72.12 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
9 | 8.3.2 | Interface with utility control/dispatch systems | Utility interface (SCADA points list, ICCP/dispatch) integration | Labor | LS | 1 | 750000 | 750000 | Lump Sum / Allowance | 7894.7368 | 95 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
9 | 8.3.3 | Interface with Amazon’s energy monitoring platform | Amazon energy monitoring interface integration | Labor | LS | 1 | 750000 | 750000 | Lump Sum / Allowance | 10000 | 75 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
10 | 9.1 | Pre‑Commissioning Electrical Tests | Pre-commissioning electrical tests (megger, hi-pot, continuity) | Labor | LS | 1 | 800000 | 800000 | Lump Sum / Allowance | 9411.7647 | 85 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
10 | 9.2.1 | PV array energization and staged startup | PV array energization and staged startup services | Labor | LS | 1 | 900000 | 900000 | Lump Sum / Allowance | 12000 | 75 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
10 | 9.2.2 | BESS commissioning and performance tests | BESS commissioning and performance testing services | Labor | LS | 1 | 2000000 | 2000000 | Lump Sum / Allowance | 23529.4118 | 85 | https://docs.nrel.gov/docs/fy25osti/93281.pdf
10 | 9.2.3 | SCADA and communications system testing | SCADA and communications system testing | Labor | LS | 1 | 600000 | 600000 | Lump Sum / Allowance | 6315.7895 | 95 | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks

## Source_Notes
Source Notes
Cost_Item | Source_URL | Notes
Project controls software & IT (scheduling, cost control) | https://www.bls.gov/ooh/business-and-financial/project-management-specialists.htm | Licensing + implementation + training (placeholder).
Insurance (builder's risk, GL, professional liability) during construction | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Benchmark-based placeholder; varies by contracts and risk profile.
Contingency reserve (approved budget rebalancing reserve) | Source file: Helios_Board_Status_Oct2027(1).pptx, slide 1 | Approved project budget is $500M. Rebuilt reserve equals approved budget minus base work subtotal.
Management reserve (removed; included in approved contingency total) | Source file: Helios_Board_Status_Oct2027(1).pptx, slide 1 | Prior separate management reserve removed to prevent total budget exceeding approved $500M.
Management reserve (5% of subtotal) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Owner-controlled reserve.
Land option/lease payments during development & construction | https://www.sciencedirect.com/science/article/pii/S0301421525003416 | Assume 900 acres (≈6 acres/MW for 150 MW). Lease/option rate ~$1,000/acre-year based on reported ranges.
Title, survey, easements legal work | https://docs.nlr.gov/docs/fy13osti/56290.pdf | Includes legal, title insurance, recording fees.
Baseline environmental surveys (flora/fauna, wetlands) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Environmental Impact Assessment and permitting support | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Public consultation/stakeholder engagement | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Zoning/local permit application fees | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Interconnection studies & queue deposits (utility/ISO) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Conceptual engineering (site layout, preliminary SLDs) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Permit/zoning design package preparation | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Detailed electrical & civil design (IFC drawings) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
BESS system design (specs, layout, controls interfaces) | https://docs.nrel.gov/docs/fy25osti/93281.pdf
SCADA & communications design | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Independent design reviews (Owner's Engineer) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Financial modeling and owner's cost estimation support | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
PPA negotiation legal & advisory fees | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Tax equity structuring & counsel | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Lender/financing fees and due diligence (IE, insurance advisor) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
EPC procurement strategy development | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Vendor selection process (RFQs, evaluation, site visits) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Contract negotiation & drafting (EPC, supply, O&M) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Logistics & expediting: PV/module/tracker/inverter shipping management | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Freight forwarding + expediting services (placeholder).
Logistics & expediting: BESS shipping management | https://docs.nrel.gov/docs/fy25osti/93281.pdf | Freight forwarding + expediting services (placeholder).
Temporary facilities: site offices, laydown, utilities | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Site safety setup, traffic control, access control | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Clearing and grubbing | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Unit cost placeholder; site-specific.
Mass grading and drainage features | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Parametric placeholder.
Internal roads and access improvements | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Parametric placeholder.
Pile driving for tracker foundations (labor + equipment) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Includes pile supply & driving.
Inverter station foundations | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Assume 50 inverter stations.
Substation foundations and yard prep | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Mounting structures installation labor (mechanical) | https://www.bls.gov/ooh/management/construction-managers.htm | Crew labor only; tracker hardware cost accounted separately.
Perimeter fencing and gates | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Assume ~5 miles perimeter; site-specific.
Security cameras and lighting infrastructure | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Tracker/racking hardware supply (single-axis) | https://docs.nrel.gov/docs/fy25osti/92257.pdf | Unit-cost placeholder calibrated to utility-scale PV benchmarks.
PV module installation labor | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm | Crew labor only.
PV modules supply (bifacial ~530W modules) | https://docs.nrel.gov/docs/fy25osti/92257.pdf | Module cost derived from utility-scale PV benchmark; actual procurement depends on market/tariffs.
Module stringing and torquing labor | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
DC cabling, combiner boxes, junction boxes (supply) | https://docs.nrel.gov/docs/fy25osti/92257.pdf
Central inverters (supply) | https://docs.nrel.gov/docs/fy25osti/92257.pdf | Assume 50 inverter units total.
Inverter equipment installation labor | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
Electrical installation labor (DC/AC collection) | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
Medium-voltage cabling and terminations (supply) | https://docs.nrel.gov/docs/fy25osti/92257.pdf
Pad-mounted transformers and main step-up transformers (supply) | https://docs.nrel.gov/docs/fy25osti/92257.pdf
Main power transformer (supply) | https://docs.nrel.gov/docs/fy25osti/92257.pdf
Substation installation labor (erection, wiring, testing support) | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm
Switchgear, protection, relays (supply) | https://docs.nrel.gov/docs/fy25osti/92257.pdf
Control house & auxiliary systems (supply) | https://docs.nrel.gov/docs/fy25osti/92257.pdf
Transmission line / tie-in works (materials + contractors) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
BESS battery containers/packs (supply) | https://docs.nrel.gov/docs/fy25osti/93281.pdf | Component of total installed cost; placeholder split.
BESS installation labor (containers, PCS, cabling) | https://www.bls.gov/ooh/construction-and-extraction/electricians.htm | ≈$20M total labor allocated over 600,000 kWh.
BESS transformers and switchgear (supply) | https://docs.nrel.gov/docs/fy25osti/93281.pdf
BESS power conversion system (PCS) (supply) | https://docs.nrel.gov/docs/fy25osti/93281.pdf
Battery management system (BMS) + EMS/controls (supply) | https://docs.nrel.gov/docs/fy25osti/93281.pdf
BESS HVAC, fire protection, and safety systems (supply + install) | https://docs.nrel.gov/docs/fy25osti/93281.pdf
SCADA servers, RTUs/PLCs, meters, weather station (supply) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Communications network (fiber, switches, radios) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Integrate PV and BESS controls (engineering + configuration) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Utility interface (SCADA points list, ICCP/dispatch) integration | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Amazon energy monitoring interface integration | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Pre-commissioning electrical tests (megger, hi-pot, continuity) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
PV array energization and staged startup services | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
BESS commissioning and performance testing services | https://docs.nrel.gov/docs/fy25osti/93281.pdf
SCADA and communications system testing | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Grid interconnection witness tests, relay settings, compliance | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Network upgrades / interconnection facilities (utility scope allowance) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks | Highly site/utility dependent; placeholder allowance.
As-built drawings, redlines, final documentation | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Initial spares & O&M tools (recommended spares kit) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Training & knowledge transfer (PV + BESS + SCADA) | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Demobilization, cleanup, closeout admin | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
Warranty reserve / punch list corrections allowance | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks

## Contingency_Control
Project Helios Budget & Contingency Control
Purpose: reconcile the workbook to the board-status PowerPoint budget and prevent the reserve from being front-loaded.
Metric | Value | Method / Source | Notes
Approved project budget | 500000000 | PowerPoint title slide | Controls the rebuilt workbook total.
Base work subtotal | 473148000 | Existing workbook total less prior contingency and management reserve | Direct and soft-cost work packages before reserve.
Rebuilt contingency reserve | 26852000 | Approved budget minus base work subtotal | This replaces the prior 10% contingency plus 5% management reserve load.
Effective contingency rate | 5.675% | Rebuilt reserve divided by base work subtotal | Shown for explanation in the presentation.
Prior reserve load | 70972200 | Prior contingency + management reserve in workbook | Was 47.3148M contingency + 23.6574M management reserve.
Reserve removed | 44120200 | Prior reserve load minus rebuilt reserve | Amount eliminated to match the PowerPoint budget.
Rebuilt workbook total | 500000000 | Base work subtotal plus rebuilt reserve | Should equal the approved project budget.
Monthly treatment | Reserve spread from Nov 2026 through Dec 2030 | Task_Budget_Clean row 7 | Prevents the old one-month $77M front-load.