## Contractor Quilt (2)
HELIOS PROJECT — CONTRACTOR QUILT
Work Activity | Plan / Define Scope | Study / Permit | Design | Procure / Contract | Financing | Construct / Install | Testing / Commissioning / Energization | Handover / Operate
Project governance & controls | Amazon | Amazon |  | Amazon | Amazon |  |  | Amazon
Land, leases & access |  | Terracon |  |  | Amazon & JPMorgan Chase
Environmental & local permitting |  |  | Sargent & Lundy
Interconnection & utility interface | [5 empty] | Primoris Services | Intertek
Roads, drainage, fencing & security | [5 empty] | MasTec Renewables
Tracker/racking foundations & structures
PV modules & DC collection | [5 empty] | Primoris Services | Intertek
Inverters & AC collection
Substation & transmission tie
BESS block
SCADA, communications & controls
Commercials: PPA, financing & tax equity
Operations & maintenance & closeout
Contractor | Contract Type
Terracon | Cost-plus-fixed-fee
Sargent & Lundy | Fixed-price-incentive-fee
JPMorgan Chase | Time and material
MasTec Renewables | Fixed-price-economic-price-adjustment
Primoris Services | Fixed-price-economic-price-adjustment
Intertek | Fixed-price-incentive-fee

## Legend (2)
Contractor | Contract Type
Terracon | Cost-plus-fixed-fee | Terracon handles the environmental studies, geotechnical work, and FEED permitting — activities where the full scope is unknown at the start
Sargent & Lundy | Fixed-price-incentive-fee | Sargent & Lundy is doing detailed electrical and civil design — work that is well-defined enough to price, but where speed and quality matter enormously to the project schedule. A fixed-price-incentive-fee contract sets a firm ceiling on cost (protecting Helios from overruns) while offering Sargent & Lundy a financial bonus if they deliver under budget or ahead of schedule.
JPMorgan Chase | Time and material | JPMorgan Chase is handling tax equity structuring, financial modeling, and financing advisory — work that is highly advisory in nature and where the level of effort depends entirely on how negotiations unfold. You can't write a fixed-price contract for investment banking advisory because the number of investor meetings, term sheet revisions, and deal structuring iterations is unpredictable.
MasTec Renewables | Fixed-price-economic-price-adjustment | MasTec is doing civil and structural construction — earthworks, pile driving, foundations, fencing — a large, multi-year scope that starts in 2028 and runs through 2029. The fixed-price element gives Helios budget certainty for the biggest spend category on the project. But because construction spans multiple years, raw material costs (steel, concrete, fuel) can shift significantly due to inflation or supply chain disruptions
Primoris Services | Fixed-price-economic-price-adjustment | Primoris mirrors MasTec's contract structure for the same fundamental reasons — they're doing the electrical and BESS installation, another large multi-year construction package running from 2028 into 2030. Electrical equipment (copper, semiconductors, inverter components) is particularly exposed to commodity price volatility. The fixed-price base gives cost certainty for the owner while the economic price adjustment protects Primoris from absorbing uncontrollable market swings on materials they must purchase 12–18 months in advance.
Intertek | Fixed-price-incentive-fee | Intertek handles commissioning, testing, and grid interconnection acceptance — work with a well-defined scope (specific test protocols required by PJM and Dominion) but where speed is critical. Every day commissioning drags past the planned window is a day closer to PPA penalty territory.

## Contractor Quilt
HELIOS PROJECT — CONTRACTOR QUILT
Work Activity | Project Management | Terracon FEED & Permitting | Sargent & Lundy C — Detailed Design | Amazon Procurement & PPA | JPMorgan Chase Financing | MasTec Renewables Civil & Structural | Primoris Services Electrical & BESS | Intertek Commissioning | Black & Veatch O&M & Closeout
WBS 1 — Project Management & Governance
Project Initiation & Charter | ● | ● | ● |  | ●
Project Governance & Controls | ● | ● | ● | ● | ● | ● | ● | ● | ●
Risk & Issue Management | ● | ● | ● | ● | ● | ● | ● | ● | ●
Project Administration | ● |  |  | ●
WBS 2 — Site Control, Environmental & Permitting
Site Identification & Feasibility | ● | ● |  |  | ●
Land Acquisition & Rights | ● | ● |  |  | ●
Environmental Studies & EIA | ● | ● | ●
Zoning & Local Permits | ● | ● | ●
Interconnection Application (PJM) | ● | ● | ● |  | ● |  |  | ●
WBS 3 — Engineering & Design
Conceptual Design | ● | ● | ● |  | ●
Permit / Zoning Design Package | ● | ● | ●
Detailed Electrical & Civil Design | ● | ● | ● |  |  | ● | ●
BESS System Design | ● |  | ● | ● |  |  | ●
SCADA & Communications Design | ● |  | ● | ● |  |  | ●
Design Reviews & Approvals | ● | ● | ● |  | ● | ● | ● | ●
WBS 4 — Financing, PPA & Tax Equity
Financial Modeling | ● |  |  | ● | ●
Power Purchase Agreement (Amazon) | ● |  |  | ● | ●
Tax Equity & Capital Structure | ● |  |  |  | ●
Financial Close | ● |  |  | ● | ●
WBS 5 — Procurement & Contracting
Procurement Strategy & EPC Packages | ● |  | ● | ● |  | ● | ●
Vendor Selection | ● |  | ● | ● |  | ● | ●
EPC Contracting | ● |  |  | ● | ● | ● | ●
Expediting & Logistics | ● |  |  | ● |  | ● | ●
Monitor Equipment Manufacturing | ● |  |  | ● |  |  | ●
WBS 6 — Civil & Structural Works
Site Mobilization & Temp Facilities | ● |  |  | ● |  | ●
Earthworks & Roads | ● | ● | ● | ● |  | ●
Pile Driving & Foundations | ● | ● | ● |  |  | ●
Mounting Structures Installation | ● |  | ● | ● |  | ● | ●
Fencing & Security | ● |  |  | ● |  | ●
WBS 7 — Electrical Systems & BESS
PV Module & DC System Installation | ● |  | ● | ● |  | ● | ●
Inverters, Transformers & AC Collection | ● |  | ● | ● |  | ● | ●
Substation & Interconnection | ● |  | ● | ● |  | ● | ● | ●
Battery Energy Storage (BESS) | ● |  | ● | ● |  |  | ● | ●
SCADA, Communications & Controls | ● |  | ● | ● |  |  | ● | ●
WBS 8–9 — Testing & Commissioning
Pre-Commissioning Electrical Tests | ● |  | ● |  |  | ● | ● | ●
System Commissioning | ● |  | ● |  |  | ● | ● | ●
Grid Interconnection (Dominion/PJM) | ● |  | ● |  | ● |  | ● | ●
Inspections & Permits Closeout | ● | ● | ● |  |  | ● | ● | ●
WBS 10 — Handover & Closeout
As-Built Documentation | ● |  | ● |  |  | ● | ● | ● | ●
O&M Setup & Training | ● |  |  | ● |  |  | ● | ● | ●
Project Closeout | ● |  |  | ● | ● |  |  | ● | ●

## Legend
Contractor Legend — Helios Project
| Company | Role / Package | Type
| Turner & Townsend & Project Helios | Owner PM / Project Management | Owner PM
| Terracon | B — FEED & Permitting | Contracted
| Sargent & Lundy | C — Detailed Design | Contracted
| Amazon | Procurement & PPA | Contracted
| JPMorgan Chase | D — Financing | Contracted
| MasTec Renewables | E — Civil & Structural | Contracted
| Primoris Services | F — Electrical & BESS | Contracted
| Intertek | G — Commissioning | Contracted
| Black & Veatch | H — O&M & Closeout | Contracted